## Project Info
Project name | Riverside Station Refurbishment
Client | Riverside Rail Ltd
Start date | 2026-04-01
End date | 2027-03-31
Data date | 2026-09-30
Currency | GBP
Prepared by | Ajay Singh

## Budget
Baseline Budget (£)
WP ID | Work package | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
WP01 | Design and Surveys | 60000 | 50000 | 40000 | 20000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
WP02 | Enabling Works | 0 | 20000 | 40000 | 40000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000
WP03 | Civils and Structures | 0 | 0 | 40000 | 80000 | 120000 | 140000 | 140000 | 120000 | 60000 | 0 | 0 | 0 | 700000
WP04 | Mechanical and Electrical | 0 | 0 | 0 | 0 | 40000 | 80000 | 100000 | 120000 | 120000 | 100000 | 40000 | 0 | 600000
WP05 | Fit-out and Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 100000 | 120000 | 140000 | 120000 | 70000 | 600000
WP06 | Testing and Handover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 40000 | 80000 | 60000 | 200000
Monthly Total |  | 60000 | 70000 | 120000 | 140000 | 190000 | 220000 | 290000 | 340000 | 320000 | 280000 | 240000 | 130000 | 2400000
Cumulative Budget |  | 60000 | 130000 | 250000 | 390000 | 580000 | 800000 | 1090000 | 1430000 | 1750000 | 2030000 | 2270000 | 2400000
Check (should be 0) | [13 empty] | 0

## Actuals
Actual Cost (£)
WP ID | Work package | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | Total
WP01 | Design and Surveys | 62000 | 55000 | 45000 | 25000 | 12000 | 5000 | [6 empty] | 204000
WP02 | Enabling Works | 0 | 18000 | 45000 | 52000 | 30000 | 10000 | [6 empty] | 155000
WP03 | Civils and Structures | 0 | 0 | 30000 | 65000 | 100000 | 115000 | [6 empty] | 310000
WP04 | Mechanical and Electrical | 0 | 0 | 0 | 0 | 35000 | 75000 | [6 empty] | 110000
WP05 | Fit-out and Finishes | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
WP06 | Testing and Handover | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
Monthly total |  | 62000 | 73000 | 120000 | 142000 | 177000 | 205000 | 0 | 0 | 0 | 0 | 0 | 0 | 779000
Cumulative actual |  | 62000 | 135000 | 255000 | 397000 | 574000 | 779000 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Check (should be 0) | [13 empty] | 0

## Forecast
Forecast (£)
Inputs: forecast of remaining cost (Oct-26 onwards)
WP ID | Work package | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | ETC
WP01 | Design and Surveys | [6 empty] | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
WP02 | Enabling Works | [6 empty] | 5000 | 0 | 0 | 0 | 0 | 0 | 5000
WP03 | Civils and Structures | [6 empty] | 120000 | 130000 | 100000 | 60000 | 0 | 0 | 410000
WP04 | Mechanical and Electrical | [6 empty] | 90000 | 110000 | 110000 | 100000 | 60000 | 20000 | 490000
WP05 | Fit-out and Finishes | [6 empty] | 0 | 60000 | 100000 | 130000 | 160000 | 150000 | 600000
WP06 | Testing and Handover | [6 empty] | 0 | 0 | 0 | 20000 | 60000 | 120000 | 200000
Outturn: actual to date + forecast
WP ID | Work package | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | EAC
WP01 | Design and Surveys | 62000 | 55000 | 45000 | 25000 | 12000 | 5000 | 3000 | 0 | 0 | 0 | 0 | 0 | 207000
WP02 | Enabling Works | 0 | 18000 | 45000 | 52000 | 30000 | 10000 | 5000 | 0 | 0 | 0 | 0 | 0 | 160000
WP03 | Civils and Structures | 0 | 0 | 30000 | 65000 | 100000 | 115000 | 120000 | 130000 | 100000 | 60000 | 0 | 0 | 720000
WP04 | Mechanical and Electrical | 0 | 0 | 0 | 0 | 35000 | 75000 | 90000 | 110000 | 110000 | 100000 | 60000 | 20000 | 600000
WP05 | Fit-out and Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 100000 | 130000 | 160000 | 150000 | 600000
WP06 | Testing and Handover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 60000 | 120000 | 200000
Monthly total |  | 62000 | 73000 | 120000 | 142000 | 177000 | 205000 | 218000 | 300000 | 310000 | 310000 | 280000 | 290000 | 2487000
Cumulative forecast |  | 62000 | 135000 | 255000 | 397000 | 574000 | 779000 | 997000 | 1297000 | 1607000 | 1917000 | 2197000 | 2487000
Check (should be 0) | [13 empty] | 0

## Cost summary
Cost Summary at Data Date (£)
WP ID | Work package | Budget (BAC) | Budget to date | Actual to date | Variance to date | EAC | Variance at completion | VAC % | Status
WP01 | Design and Surveys | 180000 | 180000 | 204000 | -24000 | 207000 | -27000 | -15% | Red
WP02 | Enabling Works | 120000 | 120000 | 155000 | -35000 | 160000 | -40000 | -33.33% | Red
WP03 | Civils and Structures | 700000 | 380000 | 310000 | 70000 | 720000 | -20000 | -2.857% | Amber
WP04 | Mechanical and Electrical | 600000 | 120000 | 110000 | 10000 | 600000 | 0 | 0% | Green
WP05 | Fit-out and Finishes | 600000 | 0 | 0 | 0 | 600000 | 0 | 0% | Green
WP06 | Testing and Handover | 200000 | 0 | 0 | 0 | 200000 | 0 | 0% | Green
Total |  | 2400000 | 800000 | 779000 | 21000 | 2487000 | -87000 | -3.625% | Amber
Check (should be 0) | [5 empty] | 0

## Change Log
Change Log
Change ID | Date raised | WP ID | Work package | Description | Reason | Cost impact (£) | Status | Approved by | Date approved
CR001 | 2026-06-15 | WP02 | Enabling Works | Unforeseen utility diversion during enabling works | Site condition | 35000 | Approved | Project Sponsor | 2026-06-30
CR002 | 2026-08-20 | WP01 | Design and Surveys | Additional surveys requested by client | Client request | 25000 | Approved | Project Sponsor | 2026-09-05
CR003 | 2026-09-25 | WP03 | Civils and Structures | Extended working hours to recover civils delay | Programme recovery | 20000 | Proposed
Original budget (baseline) | 2400000
Approved changes | 60000
Current approved budget | 2460000
EAC | 2487000
Variance vs current budget | -27000
Pending changes (proposed) | 20000

## Risk Register
Risk Register
Risk ID | Date raised | WP ID | Work package | Description | Owner | Likelihood (1-5) | Impact (1-5) | Score | Rating | Cost exposure (£) | Probability | Expected value (£) | Mitigation | Status
R001 | 2026-09-01 | WP03 | Civils and Structures | Poor ground conditions may delay civils works, increasing cost | Civils Manager | 4 | 4 | 16 | High | 60000 | 50% | 30000 | Extra ground investigation ahead of works | Open
R002 | 2026-09-05 | WP04 | Mechanical and Electrical | Long lead time on switchgear may delay M&E installation | M&E Manager | 3 | 4 | 12 | Medium | 40000 | 40% | 16000 | Order early and identify a backup supplier | Open
R003 | 2026-09-10 | WP05 | Fit-out and Finishes | Upstream delays may compress fit-out, needing overtime | Project Manager | 3 | 3 | 9 | Medium | 30000 | 30% | 9000 | Resequence works and agree weekend working | Open
R004 | 2026-09-15 | WP06 | Testing and Handover | Rail operator may refuse the testing possession window | Project Manager | 2 | 5 | 10 | Medium | 50000 | 20% | 10000 | Book possessions early with the operator | Open
R005 | 2026-05-01 | WP02 | Enabling Works | Further unrecorded utilities may be found during enabling works | Enabling Lead | 1 | 3 | 3 | Low | 20000 | 10% | 2000 | Utility survey before excavation | Closed
Open risk exposure (expected value) | 65000
EAC | 2487000
Risk-adjusted EAC | 2552000
Current approved budget | 2460000
Risk-adjusted variance | -92000
Open high risks | 1

## Dashboard
Riverside Station Refurbishment: Cost Dashboard
Data date | 2026-09-30
Original budget | 2400000
Current approved budget | 2460000
Actual to date | 779000
EAC | 2487000
Variance vs current budget | -27000
Risk-adjusted EAC | 2552000
Open high risks | 1
Overall status | Amber
Month |  | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
Budget |  | 60000 | 130000 | 250000 | 390000 | 580000 | 800000 | 1090000 | 1430000 | 1750000 | 2030000 | 2270000 | 2400000
Actual |  | 62000 | 135000 | 255000 | 397000 | 574000 | 779000 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Forecast |  | 62000 | 135000 | 255000 | 397000 | 574000 | 779000 | 997000 | 1297000 | 1607000 | 1917000 | 2197000 | 2487000
Work package | Variance at completion
Design and Surveys | -27000
Enabling Works | -40000
Civils and Structures | -20000
Mechanical and Electrical | 0
Fit-out and Finishes | 0
Testing and Handover | 0
Position at 30 September 2026: £779k has been spent against £800k planned. The project is forecast to finish at £2.487m, which is £27k (1.1%) over the current approved budget of £2.46m.
Drivers: most of the overrun against the original budget is covered by £60k of approved changes for Design and Enabling Works. The remaining variance is mainly Civils (£20k), which is behind schedule, and that delay is pushing Fit-out and Testing later. Civils' underspend to date reflects the delay, not a saving.
Risk: including open risks, the risk-adjusted outturn is £2.552m (£92k over), with poor ground conditions on Civils (R001) the largest exposure.
Actions: decide on CR003 (£20k civils recovery), which would reduce the variance to £7k if approved; carry out additional ground investigation to reduce R001; and monitor the knock-on delay to Fit-out and Testing.